## Team Overview
Project Overview Court Judgments - Making Insights from Unstructured Text Data
Project | Use case 3: Turn Court judgments into Structured insights |  | 6 Gramss - Team 4 |  |  | To be Started
Start date | 23-Sep (7:00 pm) |  |  |  |  | In-Progress
Deadline | 25-Sep (11:00 am) |  |  |  |  | Complete
Status | Complete |  |  |  |  | On-hold/Cancelled
Team Structure |  |  | Sprint Meetings (Notes/Target for Next Meetings - INSPECT & ADAPT)
Name | Role | GitHub | Spint Targets for 1 pm call | Spint Target for 5 pm call | Spint Target for 8 pm call
Sam | Data Engineer | engleangs | fix dev Ops issue complete the ETL data extraction (work with Simon) | complete AWS implementation | review implementation complete
Anchit | Project Manager/ Cloud Engineer | Anchitsood2021 | review project plan (updated), req doc, RAID logs start working on ETL( Review the code from Simon and Sam) work on data format , review snowflake & database schema (with Radiya and Greg) Work with greg, radiya and Sam for the implementaiton | - review dbt implementation - proceed with roles and permissions in Snowflake env - update project documentation | -complete the implementation on roles and permissions for Snowflake - update project documentation
Greg | Analytics Engineer | ysadore | finalize format for json, build scripts and sample data for sample visualizations | - made ingestion agent in snowflake - helped E Sam with access problems - was mostly blocked on other things | - dbt implementation
Radiya | Data Analyst | RadiyaBintaReza | finalize format for json, build scripts and sample data for sample visualizations | Create dashboard sharing insights | Fix issues and review dashboard
Simon | Data Engineer | Simonswlin | to deploy streamlit ui to a local link that we can all use to input pdf files for analysis |  | -----
Minh | Cloud Engineer | HienMing58 | (absent) was working on CI/CD pipeline on 23rd Sep | (absent) | (absent)
IMPORTANT PROJECT LINKS
Name | Link
Application Link (starting point of workflow) | https://datathon.someaknea.com/
Final Report URL | https://app.snowflake.com/streamlit/jevvupu/bf88439/#/apps/rbjh7ksd5iacpf7jcrqy
JIRA board | https://team6gramss.atlassian.net/jira/software/projects/SCRUM/boards/1
GitHub Repo | https://github.com/engleangs/datathon/tree/main
Snowflake URL | https://app.snowflake.com/ap-southeast-6.aws/tz25487/#/homepage
Source PDFs | https://www.courtsofnz.govt.nz/judgments/high-court
Input/sample PDFs | data - Google Drive
Tracker | Purpose
Tasks - JIRA Scrum BOARD | Assign owner, sequence work and record done criteria
RAID | Manage risks, assumptions, issues and dependencies
Project plan | Project planned timelines per milestones and Review sprint progress as per plan

## MVP Requirements + Design
S.No. | Requirements (Team name: 6GRAMSS) | MoSCoW | Team member | Role | Access | Sees names of individuals?
1 | High-level Requirement: Choose court proceedings related data document (PDF) as source PDF and load them into Snowflake. Build a proof of concept that extracts useful information into a structured format. Make each result traceable to its source document and supporting text. | Must Have | Data Engineer | DTH_DATA_ENGINEER | Build: create tables, stages and schemas; read and change data | Yes
2 | PDFs (as raw dataset) are taken from courtsofnz.govt.nz (High Court, Govt website) Link: https://www.courtsofnz.govt.nz/judgments/high-court | Must Have | Analytics Engineer | DTH_ANALYTICS_ENGINEER | Build | Yes
3 | From a user interface, raw dataset in the form of PDFs (unstructured data/text - court data) will be uploaded. | Must Have | Data Scientist | DTH_DATA_SCIENTIST | Write: read and change rows, no new tables; Cortex | Yes
4 | Raw dataset will be then converted from unstructured text format to a structured format in json. | Must Have | Data Analyst | DTH_DATA_ANALYST | Read, plus create the Streamlit app in COURTLENS | No (masked)
5 | Structured data will be pushed to Snowflake environment and relevant configurations will be completed to implement data analysis and visualizations. | Must Have | Project Manager | DTH_PROJECT_MANAGER | Read, plus open the app | No (masked)
6 | Generate insights and/or visualizations and/or recommendations from the data captured in Snowflake environment. | Must Have | Cloud Engineer | DTH_CLOUD_ENGINEER (+ keeps ACCOUNTADMIN) | Build, plus warehouse admin | Only via SYSADMIN/ACCOUNTADMIN
7 | Sample insights: duration each case takes (average) - based on case details how many times judge can change number of cases type of case (criminal vs corporate vs civil) More TBD (Greg + Radiya) | Should Have
8 | Below are the required roles and permissions for the snowflake database and schema implementation: DTH_DB_READ = SELECT on everything in DATATHON_TEST DTH_DB_WRITE = READ + change rows in DATATHON_TEST DTH_DB_BUILD = WRITE + create objects in DATATHON_TEST DTH_MART_READ = Read access to the masked MART views only (Data Analyst, pm, app dev) | Must Have | Design Wireframe/Mock-up
9 | Relevant schema and data model details have been captured in "Data Model" sheet with below assumptions. | Must Have
10 | Explore and implement ML implementation - classification of outcome prediction | Won't Have
11 | Explore ML implementation for classification of outcome prediction (classification in terms of prediction of Guilty vs Not Guilty) | Could Have
PROBLEM DEFITION: Context. NZ District Court judgments are published as text-based PDFs of multiple pages. Regulatory prosecutions are sentenced by comparison with earlier cases, where sentencing samples we reviewed cites comparable cases and their starting points. Problem. The facts that matter are buried in unstructured text/details: the court, parties, charges, starting point, discounts, fine, reparation and cited cases. The documents also vary: 1. One judgment can mention 20 or more dollar amounts, and only the court's own figures count. 2. Some documents are pre-trial rulings and not really sentencing decisions. 3. Names of victims and suppressed details are redacted. Finding and comparing outcomes today means reading every document by hand.
SOLUTION: An ingestion agent parses each PDF, extracts the fields and loads them into Snowflake (DATATHON_TEST.COURTLENS), following the team's data model (Case, Decision, Court, Location, Judge, Party, Counsel, Citation). The team validates the results, publishes masked secure views in a MART schema and on application's UJI, and builds a Streamlit dashboard on those views. Role-based access controls who can see what.

## Project Plan & Sprint Meetings
Milestones | Timeline | Status
Kick-off (choose use-case, plan and understand requirments) | 23-Sep, 7 pm | Complete | SCRUM CONNECT #1 (SPRINT PLANNING)
Build UI | 2026-09-23 | Complete
Complete GitHub configuration | 24-sep, 10 am | Complete
ETL and deployment pipeline | 24-sep, 10 am | Complete
Complete Feature to extract from PDF document and convert to structured data | 24-sep, 3 pm | Complete
Snowflake and dbt implementation | 24-sep, 7:30 pm | Complete
Build visualizations and insights | 24-Sep, 8 pm | Complete | SCRUM CONNECT #2 (SPRINT Progress Review) (inspect & Adapt)
Test full process- WORKING DEMO | 24-Sep, 9:30 pm | Complete
Presentation Completion | 24-Sep, 11:00 pm | Complete
SCRUM CONNECT #3 (SPRINT Progress Review) (inspect & Adapt)
SCRUM CONNECT #4 (SPRINT PLANNING)
FINAL SPRINT REVIEW & RETRO (SPRINT Progress Review) (inspect & Adapt)

## RAID Logs
ID | Type | Description | Consequence / impact | Owner | Likelihood (1–5) | Impact (1–5) | Score | Rating | Mitigation / action | Status | Raised | Closed Date | Trigger | Contingency | Linked tasks
R01 | Risk | Bedrock model access not granted, or blocked in the trial | No LLM extraction; demo loses its AI component | Simon | 4 | 5 | 20 | Red | Test in the first hour (T05) | Complete | 2026-09-24 | 2026-09-24 | No successful call by M1 | Cortex AI_COMPLETE (T26); last resort rules only
R02 | Risk | Scope creep: too many fields, pages or charts | Must features unfinished | Anchit | 4 | 4 | 16 | Red | MoSCoW priorities; feature freeze 09:30 | Complete | 2026-09-24 | 2026-09-24 | Money-field accuracy < 80% on gold set | Route to REVIEW; narrow to 4 fields
R03 | Risk | 11:00 code deadline missed | Code deliverable missed | Anchit | 3 | 5 | 15 | Red | Milestones and timeboxes; code freeze 1 day early by 24th Sep, 10:00 pm | Complete | 2026-09-24 | 2026-09-24 | New feature proposed after M4 | Park it in the roadmap
R04 | Risk | Privacy: suppressed names or victim details exposed | Privacy breach; responsible-AI score hit | Simon | 2 | 5 | 10 | Amber | Keep redactions; never extract victim/witness details; flag suppression orders | Complete | 2026-09-24 | 2026-09-24 | M5 more than 1 h late | Cut Should/Could tasks; demo on gold set
R05 | Risk | Agent now has access to delete data and change whatever it wants in all the schemas it can access | Missing or wrong fields for some documents | Greg | 5 | 3 | 15 | Red | Implement roles and permissions and review database and schema to ensure impact is minimized in transactions | Complete | 2026-09-24 | 2026-09-24 | Rule accuracy < 95% on gold set | Send failing fields to LLM at REVIEW tier
R05 | Risk | Merge conflicts break main branch | Blocked merges; lost time | Sam | 3 | 2 | 6 | Green | Small PRs; CI on every PR; peer review of merge pull request after review | Complete | 2026-09-24 | 2026-09-24 | > 5% of quotes fail verification | Fuzzy match; check neighbouring paragraphs
R06 | Risk | A team member is unavailable | Tasks stall | Anchit | 2 | 3 | 6 | Green | Review team availability for the next two days and assign Named backup per role as needed | Complete | 2026-09-24 | 2026-09-24 | Reviewer cannot explain a PR | Rewrite simpler before merging
R07 | Risk | Code deadline is 25 Sep 11:00 am; presentation later that day | If wrong: Timeline must shift | Anchit | 1 | 5 | 5 | Green | communicate with team regularly to check on the submission timelines or any updates | Complete | 2026-09-24 | 2026-09-24
R08 | Risk | Implementations by other members may impact or override anyone else' work | If wrong: Timeline must shift | Anchit | 3 | 4 | 12 | Amber | communicate with team regularly when working on similar functionalities, do peer implementation reviews, share updates in regular scrum calss | Complete | 2026-09-24 | 2026-09-24 | Any failure in rehearsal | Recorded video and screenshots
A01 | Assumption | Snowflake and AWS trial accounts come with admin rights | If wrong: Setup blocked until access fixed | [6 empty] | Complete | 2026-09-24 | 2026-09-24 | Non-defendant personal name in CORE | Delete row; fix prompt
A02 | Assumption | A Claude model is available on Bedrock in ap-southeast-2 or via cross-region inference | If wrong: Switch to Cortex fallback | [6 empty] | Complete | 2026-09-24 | 2026-09-24 | Not working at M1 + 30 min | Internal stage via Snowsight upload
A03 | Assumption | A case can have multiple decisions in it | [7 empty] | Complete | 2026-09-24 | 2026-09-24 | Chart group with n < 5 | Show counts, hide averages
A04 | Assumption | A case will be heard in one court and one location only | [7 empty] | Complete | 2026-09-24 | 2026-09-24 | Downloads unfinished at M2 | Continue with minimum 20
A05 | Assumption | A decision will have only one legal officer presiding over it (possibly dubious) | [7 empty] | Complete | 2026-09-24 | 2026-09-24 | CI red on main > 30 min | Revert last merge
A06 | Assumption | Multiple citations can be made in a single decision | [7 empty] | Complete | 2026-09-24 | 2026-09-24 | Absent > 1 h at a milestone | Backup takes over the task
A07 | Assumption | A decision can have multiple counsels engaged in it, and a counsel might be engaged in many decisions (ie, multiple decisions over the same case | [7 empty] | Complete | 2026-09-24 | 2026-09-24
A08 | Assumption | A counsel need not be engaged for all the decisions in a case | [7 empty] | Complete | 2026-09-24 | 2026-09-24
A09 | Assumption | A party can be engaged in multiple cases, and multiple case can have multiple parties engaged in it (ie, defendant and accuser) | [7 empty] | Complete | 2026-09-24 | 2026-09-24
A10 | Assumption | A counsel can be represent multiple parties, and a party might be represented by multiple counsels | [7 empty] | Complete | 2026-09-24 | 2026-09-24
I01 | Issue | Issue with CICD pipeline with github, access issue with .env credential on AWS problem |  | Sam |  |  |  |  | create new AWS IMA User and assign correct access | Complete | 2026-09-24 | 2026-09-24
I02 | Issue | problem with configuring AWS Bedrock model as all Anthropic AI models were not working |  | Sam |  |  |  |  | Try using deep seek model or Nova 2 Lite LLM | Complete | 2026-09-24 | 2026-09-24
I03 | Issue | Problem in extraction data. DeepSeek models do not recognize pattern of some of the data cases |  | Simon |  |  |  |  | Explore other model on AWS bedrock and found this work : global.amazon.nova-2-lite-v1:0 | Complete | 2026-09-24 | 2026-09-24
I04 | Issue | Issue with incorrect access rights on snowflake db |  | Greg |  |  |  |  | Double check and grant correct permission on users, db and schema on snowflake | Complete | 2026-09-24 | 2026-09-24
D01 | Dependency | Schema frozen (T12, T21) before prompt, validation and app work | Greg | [5 empty] | Chase owner at each stand-up | Complete | 2026-09-24 | 2026-09-24
D02 | Dependency | GitHub access for all 6 members | Anchit | [5 empty] | Chase owner at each stand-up | Complete | 2026-09-24 | 2026-09-24
D04 | Dependency | Data and insights implementation in Snowflake depends on AWS configuration and UI implementation | [6 empty] | Agree on data format/structure and Work with mock data initially while the first part of implementation is built | Complete | 2026-09-24 | 2026-09-24
D05 | Dependency | Snowflake agent implementation dependent on AWS and pipeline implementation | [6 empty] | Agree on data format/structure and Work with mock data initially while the first part of implementation is built | Complete | 2026-09-24 | 2026-09-24
T23, T24
T11
T10
T24, T38
T22, T27, T31
All tasks
T44–T46
| Risk | LLM Model expected not working with code
Sam
Sam
Sam
Sam
Sam

## Team Progress View- JIRA SCRUM
TEAM JIRA SCRUM BOARD (FINAL-SPRINT VIEW) (story points estimated (1/2/3); priority updated; epic, story and tasks updated & closed; sprint completed, etc.) |  | JIRA DASHBOARD - TEAM 6GRAMSS | Sprint Completion - Agile Custom Reports | TEAM JIRA BOARD: MID-SPRINT VIEW
SPRINT DETAILS (Start and End Timelines) | EPIC- TIMELINE View

## JIRA Task Breakdown
Epic Key | Epic | Item Key | Type | Summary | Owner | Priority | Status | Start Date | Due Date
SCRUM-36 | Plan and set up (kick-off, requirements, GitHub, cloud access) | SCRUM-36 | Epic | Plan and set up (kick-off, requirements, GitHub, cloud access) | Anchit | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-36 | Plan and set up (kick-off, requirements, GitHub, cloud access) | SCRUM-1 | Task | Project Planning document (BRD) | Anchit | High | Done | 2026-09-23 | 2026-09-25
SCRUM-36 | Plan and set up (kick-off, requirements, GitHub, cloud access) | SCRUM-15 | Story | PM: Project Plan Creation | Anchit | High | Done | 2026-09-23 | 2026-09-25
SCRUM-36 | Plan and set up (kick-off, requirements, GitHub, cloud access) | SCRUM-26 | Task | Set up AWS Bedrock Account | Simon Lin | High | Done | 2026-09-23 | 2026-09-25
SCRUM-36 | Plan and set up (kick-off, requirements, GitHub, cloud access) | SCRUM-17 | Story | PM: Document requirements, RAID logs, track task and project progress | Anchit | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-36 | Plan and set up (kick-off, requirements, GitHub, cloud access) | SCRUM-16 | Story | Fix issues of Devopt | Engleang Sam | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-36 | Plan and set up (kick-off, requirements, GitHub, cloud access) | SCRUM-30 | Task | Submit support ticket AWS | Simon Lin | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-36 | Plan and set up (kick-off, requirements, GitHub, cloud access) | SCRUM-3 | Task | Dbt implementation/configuration | Anchit | Low | Cancelled | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-14 | Epic | Develop and deploy project | Anchit | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-27 | Task | Code Streamlit UI | Simon Lin | Highest | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-19 | Story | Database/App: ingestion pipeline | Gregory Hinds | Highest | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-6 | Story | Database: build ingestion code | Gregory Hinds | Highest | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-11 | Story | Database: finalise data format | Radiya Binte Reza | High | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-12 | Story | Database: amend schema to align with finalised format | Gregory Hinds | High | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-21 | Story | Snowflake permissions implementation | Anchit | High | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-29 | Task | Push Streamlit UI on GitHub | Simon Lin | High | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-8 | Story | Database: ingest test data | Gregory Hinds | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-13 | Story | Database: create/build security roles | Anchit | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-18 | Story | Database: make DBT project | Gregory Hinds | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-20 | Story | Fix issues of Snowflake schema | Engleang Sam | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-23 | Task | Data collection: input | Simon Lin | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-28 | Task | Run test cases on Streamlit app | Simon Lin | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-33 | Story | Enable duplicate detection | Gregory Hinds | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-35 | Task | Snowflake: create/update permissions for roles | Anchit | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-38 | Task | Create roles: Snowflake database and schema | Anchit | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-5 | Story | Database: define enumerations | Gregory Hinds | Medium | Cancelled | 2026-09-23 | 2026-09-25
SCRUM-14 | Develop and deploy project | SCRUM-7 | Story | Database: build test framework | Gregory Hinds | Medium | Cancelled | 2026-09-23 | 2026-09-25
SCRUM-37 | Insights, working demo and presentation | SCRUM-37 | Epic | Insights, working demo and presentation | Anchit | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-37 | Insights, working demo and presentation | SCRUM-9 | Story | Dashboard: write query code | Radiya Binte Reza | High | Done | 2026-09-23 | 2026-09-25
SCRUM-37 | Insights, working demo and presentation | SCRUM-10 | Story | Dashboard: build visualisations | Radiya Binte Reza | High | Done | 2026-09-23 | 2026-09-25
SCRUM-37 | Insights, working demo and presentation | SCRUM-22 | Story | Make presentation deck | Gregory Hinds | High | Done | 2026-09-23 | 2026-09-25
SCRUM-37 | Insights, working demo and presentation | SCRUM-34 | Story | Check human-review flagging works correctly | Anchit | High | Done | 2026-09-23 | 2026-09-25
SCRUM-37 | Insights, working demo and presentation | SCRUM-31 | Story | Prepare presentation | Gregory Hinds | Medium | Done | 2026-09-23 | 2026-09-25
SCRUM-37 | Insights, working demo and presentation | SCRUM-32 | Story | Prepare presentation | Anchit | Medium | Done | 2026-09-23 | 2026-09-25
EPIC-1 : Develop and deploy project | [7 empty] | EPIC-2 : Plan and set up (kick-off, requirements, GitHub, cloud access)
EPIC-3 :Insights, working demo and presentation

## Data Model
Data Model Documentation
Table | fct_judgment
Table Description | One row per judgment (source document), from its latest extraction. The central table of the model
Field | Type | Qualifiers | Comments | Description
judgment_key | varchar | not null, unique | PK | Our internal reference for the judgment (equal to document_id)
document_id | varchar | not null | FK dim_source_document | The PDF this judgment was extracted from
extraction_id | varchar | not null |  | The extraction these values came from (the latest for this document)
court_key | varchar |  | FK dim_court | The court that issued the judgment
case_category_key | varchar |  | FK dim_case_category | The category of case
case_name | varchar |  |  | The case name as extracted
neutral_citation | varchar | unique (warn) | Duplicates suggest the same judgment was uploaded twice | The judgment's own neutral citation, e.g. [2024] NZHC 123
judgment_date | date |  |  | The date of the judgment
outcome | varchar |  |  | The court's decision / outcome, as extracted
extraction_status | varchar | not null | ACCEPTED or REVIEW_REQUIRED | Result of the deterministic validation checks
agent_needs_human_review | boolean | not null |  | The agent flagged this extraction for human review
is_verified_for_default_analytics | boolean | not null |  | ACCEPTED and not flagged by the agent. Filter on this for verified-only analysis
evidence_verified | number | not null |  | Number of evidence passages matched back to the PDF
evidence_total | number | not null |  | Number of evidence passages supplied
model_id | varchar |  |  | The model that produced the extraction
extracted_at | timestamp_ntz |  |  | When the extraction was loaded
Table | dim_source_document
Table Description | One row per ingested PDF
Field | Type | Qualifiers | Comments | Description
document_id | varchar | not null, unique | PK | SHA-256 of the file
filename | varchar |  |  | The uploaded file name
source_url | varchar |  |  | Where the PDF was obtained
document_sha256 | varchar |  |  | SHA-256 of the file contents
page_count | number |  |  | Number of pages in the PDF
Table | dim_court
Table Description | One row per court. Names standardised in staging (e.g. NZHC -> HIGH COURT)
Field | Type | Qualifiers | Comments | Description
court_key | varchar | not null, unique | PK | Hash of the cleaned court name
court_name | varchar | not null |  | The name of this court
Table | dim_case_category
Table Description | One row per case category
Field | Type | Qualifiers | Comments | Description
case_category_key | varchar | not null, unique | PK | Hash of the cleaned category name
case_category_name | varchar | not null |  | The case category. Enumeration unknown
Table | dim_judge
Table Description | One row per judge. Split from the single extracted judge string, with titles (J, JJ, CJ, Justice etc) stripped
Field | Type | Qualifiers | Comments | Description
judge_key | varchar | not null, unique | PK | Hash of the cleaned judge name
judge_name | varchar | not null | Name matching is heuristic | The judge's name without title
Table | bridge_judgment_judge
Table Description | A many-to-many table between judgments and judges. Allows multi-judge panels
Field | Type | Qualifiers | Comments | Description
judgment_judge_key | varchar | not null, unique | PK | Hash of judgment_key and judge_key
judgment_key | varchar | not null | FK fct_judgment
judge_key | varchar | not null | FK dim_judge
judge_position | number |  |  | Order the judge was named in the judgment
Table | dim_topic
Table Description | One row per legal topic
Field | Type | Qualifiers | Comments | Description
topic_key | varchar | not null, unique | PK | Hash of the cleaned topic name
topic_name | varchar | not null |  | The legal topic
Table | bridge_judgment_topic
Table Description | A many-to-many table between judgments and legal topics
Field | Type | Qualifiers | Comments | Description
judgment_topic_key | varchar | not null, unique | PK | Hash of judgment_key and topic_key
judgment_key | varchar | not null | FK fct_judgment
topic_key | varchar | not null | FK dim_topic
topic_position | number |  |  | Order the topic was listed in the extraction
Table | dim_legislation
Table Description | One row per Act or regulation
Field | Type | Qualifiers | Comments | Description
legislation_key | varchar | not null, unique | PK | Hash of the cleaned Act name
act_name | varchar | not null |  | The name of the Act or regulation
Table | fct_legislation_citation
Table Description | One row per legislation reference in a judgment, with section and supporting evidence
Field | Type | Qualifiers | Comments | Description
legislation_citation_key | varchar | not null, unique | PK | Hash of judgment_key and reference_position
judgment_key | varchar | not null | FK fct_judgment
legislation_key | varchar | not null | FK dim_legislation
section | varchar |  |  | Section or provision, if stated
reference_position | number |  |  | Order the reference was listed in the extraction
evidence_page | number |  |  | 1-based PDF page containing the supporting passage
evidence_text | varchar |  |  | The supporting passage
Table | dim_cited_case
Table Description | One row per cited case, keyed on its citation
Field | Type | Qualifiers | Comments | Description
cited_case_key | varchar | not null, unique | PK | Hash of the cleaned citation
citation | varchar | not null |  | The citation of the cited case
cited_case_name | varchar |  | Most common name given across citing judgments | The cited case's name
cited_judgment_key | varchar |  | FK fct_judgment | The cited case's own judgment, when it is in the corpus (citation network)
Table | fct_case_citation
Table Description | One row per case cited in a judgment, with supporting evidence
Field | Type | Qualifiers | Comments | Description
case_citation_key | varchar | not null, unique | PK | Hash of judgment_key and reference_position
judgment_key | varchar | not null | FK fct_judgment | The citing judgment
cited_case_key | varchar | not null | FK dim_cited_case | The case being cited
reference_position | number |  |  | Order the citation was listed in the extraction
evidence_page | number |  |  | 1-based PDF page containing the supporting passage
evidence_text | varchar |  |  | The supporting passage
Table | fct_judgment_legal_issue
Table Description | One row per legal issue identified in a judgment. Free text, so not a shared dimension
Field | Type | Qualifiers | Comments | Description
legal_issue_key | varchar | not null, unique | PK | Hash of judgment_key and issue_position
judgment_key | varchar | not null | FK fct_judgment
issue_position | number |  |  | Order the issue was listed in the extraction
issue_text | varchar |  |  | The legal issue
Table | fct_judgment_quality_issue
Table Description | One row per agent uncertainty, validation reason, missing reference or publication marker
Field | Type | Qualifiers | Comments | Description
quality_issue_key | varchar | not null, unique | PK | Hash of judgment_key, issue_type and issue_position
judgment_key | varchar | not null | FK fct_judgment
issue_type | varchar |  | AGENT_UNCERTAINTY, VALIDATION_REASON, MISSING_REFERENCE or PUBLICATION_MARKER | The kind of quality issue
issue_position | number |  |  | Order within its source list
issue_text | varchar |  |  | The issue detail
Table | fct_judgment_evidence
Table Description | One row per supporting passage the agent quoted for a judgment's metadata
Field | Type | Qualifiers | Comments | Description
evidence_key | varchar | not null, unique | PK | Hash of judgment_key and evidence_position
judgment_key | varchar | not null | FK fct_judgment
evidence_position | number |  |  | Order the passage was listed in the extraction
evidence_page | number |  |  | 1-based PDF page containing the passage
evidence_text | varchar |  |  | The quoted passage
Table | fct_extraction_run
Table Description | One row per extraction attempt, including superseded ones. For comparing models / prompts over time
Field | Type | Qualifiers | Comments | Description
extraction_id | varchar | not null, unique | PK | Our internal reference for the extraction
document_id | varchar | not null | FK dim_source_document | The PDF that was extracted
model_id | varchar |  |  | The model that produced the extraction
extraction_status | varchar |  | ACCEPTED or REVIEW_REQUIRED | Result of the deterministic validation checks
agent_needs_human_review | boolean | not null |  | The agent flagged this extraction for human review
is_verified_for_default_analytics | boolean |  |  | ACCEPTED and not flagged by the agent
evidence_verified | number |  |  | Number of evidence passages matched back to the PDF
evidence_total | number |  |  | Number of evidence passages supplied
extracted_at | timestamp_ntz |  |  | When the extraction was loaded
is_latest | boolean | not null |  | This is the extraction used by fct_judgment

## Tasks (hidden)
Task | Task Owner | Secondary Owner
Build UI for dropping Pdf (UI creation) | Simon | Minh
ETL Implementation- extract data from pdf - structured data(prompt eng) and convert to structured format (output in csv/json format) - Prompt Engineering | Simon
GitHub configuration, creating pipeline for Snowflake, pushing of queries to Snowflake | Minh | Sam
configuring pipeline for Converted file to be pushed to Snowflake env | Minh | Sam
build dashboard
Generate insights from data
Generate recommendations from data
Tshirt sizing of US and tasks
Create requirement document project plan roadmap JIRA task board Risk register documents
Create team tasks- ALL
t-shirt sizing of tasks
refine requirements
technical tasks and feasibilities
resolve github workflow fix
build ui

## Team votes & Misc Info
Data | Simon | Minh | Greg | Radiya | Sam | Anchit | Likelihood | Impact |  |  |  |  | Dropdown list- Status | RAID Logs | MoSCoW
court | 1 |  | 2 | 1 | 2 | 2 |  | 1 Negligible | 2 Minor | 3 Moderate | 4 Major | 5 Severe | To Be Worked | Risk | Must Have
food | 2 | 1 |  |  |  |  | 5 Almost certain | 0 | 0 | 1 | 0 | 0 | In-Progress | Assumption | Could Have
healthcare |  | 2 |  | 2 |  |  | 4 Likely | 0 | 1 | 1 | 2 | 1 | Cancelled / On-Hold | Issue | Should Have
financial data |  |  | 1 |  | 1 | 1 | 3 Possible | 0 | 1 | 1 | 2 | 1 | Complete | Dependency | Won't Have
[7 empty] | 2 Unlikely | 0 | 0 | 2 | 1 | 1
[7 empty] | 1 Rare | 0 | 0 | 0 | 0 | 0
Rating: Red = 15–25 (act now, report every stand-up) · Amber = 8–14 (mitigation owned, checked at milestones) · Green = 1–7 (monitor)
Scoring scales
[7 empty] | Score | Likelihood
[7 empty] | 1 | Rare (< 10%)
[7 empty] | 2 | Unlikely (10–30%)
[7 empty] | 3 | Possible (30–50%)
[7 empty] | 4 | Likely (50–80%)
[7 empty] | 5 | Almost certain (> 80%, or already seen)